## Trang tính1
TASK TITLE | TASK OWNER | START DATE | DUE DATE | WEEK 1 |  |  |  |  | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [5 empty] | END
|  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
|  |  |  | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Sprint 1 (Project Initiating) |  | 2024-09-04 | 2024-09-09
Prepare and analysis project needs, project scope | All member | 2024-09-04 | 2024-09-06 | bar: WEEK 1 4 Wed to WEEK 1 6 Fri; WEEK 5 30 Mon to WEEK 5 1 Tue
Report 1 (Project Introduction) | ManhPD | 2024-09-07 | 2024-09-07 | bar: WEEK 1 7 Sat; WEEK 5 30 Mon to WEEK 5 1 Tue
Development Plan | All member | 2024-09-08 | 2024-09-08 | bar: WEEK 1 8 Sun; WEEK 5 30 Mon to WEEK 5 1 Tue
Project Schedule | All member | 2024-09-09 | 2024-09-09 | bar: WEEK 2 9 Mon; WEEK 5 30 Mon to WEEK 5 1 Tue
Project Management | All member | 2024-09-09 | 2024-09-09 | bar: WEEK 2 9 Mon; WEEK 5 30 Mon to WEEK 5 1 Tue
Report 2 (Project Plan) | ManhPD | 2024-09-09 | 2024-09-09 | bar: WEEK 2 9 Mon; WEEK 5 30 Mon to WEEK 5 1 Tue
Sprint 2 (Project General Initialization) |  | 2024-09-10 | 2024-10-10
Document |  | 2024-09-10 | 2024-10-10 | bar: WEEK 1 4 Wed to WEEK 1 8 Sun; WEEK 2 10 Tue to WEEK 6 10 Thu
Database Design | All member | 2024-09-10 | 2024-09-21 | bar: WEEK 2 10 Tue to WEEK 3 21 Sat
Usecase | All member | 2024-09-22 | 2024-09-24 | bar: WEEK 3 22 Sun to WEEK 4 24 Tue
Project Architeture Design | All member | 2024-09-25 | 2024-09-27 | bar: WEEK 4 25 Wed to WEEK 4 27 Fri; WEEK 5 30 Mon to WEEK 5 1 Tue
Functional Requirment | All member | 2024-09-28 | 2024-09-30 | bar: WEEK 4 28 Sat to WEEK 5 1 Tue
Report 3 (Software Requirment Specification) | ManhPD | 2024-10-01 | 2024-10-05 | bar: WEEK 5 30 Mon to WEEK 5 5 Sat
Report 4 (Software Design) | ManhPD | 2024-10-06 | 2024-10-10 | bar: WEEK 5 30 Mon to WEEK 5 1 Tue; WEEK 5 6 Sun to WEEK 6 10 Thu
Coding |  | 2024-10-01 | 2024-10-10
Initialize Back-end Project | ManhPD | 2024-09-23 | 2024-09-24 | bar: WEEK 4 23 Mon to WEEK 4 24 Tue
Back-end Project Common | ManhPD, AnNV | 2024-09-25 | 2024-10-10 | bar: WEEK 4 25 Wed to WEEK 6 10 Thu
Initialize Front-end Project | KietHT | 2024-09-23 | 2024-09-24 | bar: WEEK 4 23 Mon to WEEK 4 24 Tue
Front-end Project Common | KietHT, ToanDT | 2024-09-30 | 2024-10-10 | bar: WEEK 5 30 Mon to WEEK 6 10 Thu
Sprint 3 (Project Development) |  | 2024-10-11 | 2024-11-06
Document |  | 2024-10-11 | 2024-10-31 | bar: WEEK 6 11 Fri to WEEK 9 31 Thu
Test Case | KietHT | bar: WEEK 6 11 Fri to WEEK 6 12 Sat; WEEK 7 16 Wed to WEEK 7 17 Thu; WEEK 8 21 Mon to WEEK 8 22 Tue; WEEK 9 29 Tue to WEEK 9 31 Thu
Sequence Diagram | All member | 2024-10-11 | 2024-10-31 | bar: WEEK 6 11 Fri to WEEK 9 31 Thu
Coding
API | ManhPD, AnNV | 2024-10-11 | 2024-10-31 | bar: WEEK 6 11 Fri to WEEK 9 31 Thu
Unit Test API | All member | 2024-10-11 | 2024-10-31 | bar: WEEK 6 11 Fri to WEEK 9 31 Thu
Screen | KietHT, ToanDT | 2024-10-11 | 2024-10-31 | bar: WEEK 6 11 Fri to WEEK 9 31 Thu
Testing
List Test Case | KietHT | 2024-10-26 | 2024-10-31 | bar: WEEK 8 26 Sat to WEEK 9 31 Thu
Verify Test Project FMS | All member | 2024-10-21 | 2024-10-31 | bar: WEEK 8 21 Mon to WEEK 9 31 Thu
Fix Bug Project FMS | All member | 2024-10-21 | 2024-10-31 | bar: WEEK 8 21 Mon to WEEK 9 31 Thu
Sprint 4 (Project Finishing) |  | 2024-11-01 | 2024-11-09
Document |  | 2024-11-01 | 2024-11-09 | bar: WEEK 9 1 Fri to WEEK 10 9 Sat
Test Case |  | 2024-11-01 | 2024-11-09 | bar: WEEK 9 1 Fri to WEEK 10 9 Sat
Testing
List Test Case | KietHT | 2024-11-01 | 2024-11-09 | bar: WEEK 9 1 Fri to WEEK 10 9 Sat
Verify Test Project FMS | All member | 2024-11-01 | 2024-11-09 | bar: WEEK 9 1 Fri to WEEK 10 9 Sat