## Sheet1
PROJECT WORK BREAKDOWN STRUCTURE
STT | Function/Screen | Feature | Level* | Function/Screen Details | Responsible person | Planned | Status | Locs | Actual Locs
1 | Sign Up | Common | Medium | Allows users to create an account | Thành | Iteration 1 | Pending
2 | Login | Common | Complex | Enables users to log in to their account | Thành | Iteration 1 | Pending
3 | Logout | Common | Simple | Logs users out of the system | Thành | Iteration 1 | Pending
4 | View Profile | Common | Simple | Enables users to view personal details | Lâm | Iteration 1 | Pending
5 | Edit Profile | Common | Simple | Enables users to update personal details | Lâm | Iteration 1 | Pending
6 | View Home Page | Public | Complex | Displays key features and introductory info | Minh | Iteration 1 | Pending
7 | View List Court | Public | Simple | Enables users to view list court | Minh | Iteration 1 | Pending
8 | View Court Detail | Public | Simple | Shows details of a specific booking | Hùng | Iteration 1 | Pending
9 | Book Court | User | Complex | Enables users to book a court | Hùng | Iteration 1 | Pending
10 | Forgot Password | Common | Medium | Provides password recovery options | Thành | Iteration 2 | Pending
11 | Change Password | Common | Simple | Allows users to update their password | Thành | Iteration 2 | Pending
12 | Send Notifications | Common | Medium | System wil send notifications to user | Minh | Iteration 2 | Pending
13 | View Notifications List | Common | Simple | Enables users to view notifications | Minh | Iteration 2 | Pending
14 | View Booking Schedule | User, Admin | Simple | Enables users to view booking schedule | Lâm | Iteration 2 | Pending
15 | View Booking Detail | User | Simple | Shows details of a specific booking | Lâm | Iteration 2 | Pending
16 | View Booking History | User, Admin | Simple | Displays previous bookings | Hùng | Iteration 2 | Pending
17 | Manage Court | Admin | Simple | Allows owners to add/edit/delete court listings | Hùng | Iteration 2 | Pending
18 | Search and Filter Court | Public | Simple | Allows user to search and filter for court |  | Iteration3 | Pending
19 | Manage Users | Admin | Simple | Allows admin to manage user accounts |  | Iteration3 | Pending
20 | Set Availability Status | Admin | Simple | Allow manager change court status |  | Iteration3 | Pending
21 | Send Email Reminder | User, Admin | Medium | Sends reminders for upcoming bookings |  | Iteration3 | Pending
22 | Reschedule Booking | User, Admin | Medium | Enables users to update booking schedule |  | Iteration3 | Pending
23 | Cancel Booking | User, Admin | Simple | Allows users to cancel a booking |  | Iteration3 | Pending
24 | Payment intergration | User | Complex | Handles court booking payments |  | Iteration 4 | Pending
25 | Create Feedback | User | Simple | Allows user send feedback |  | Iteration 4 | Pending
26 | View Feedback | User, Admin | Simple | Allows user view feedback |  | Iteration 4 | Pending
27 | Edit Feedback | User | Simple | Allows user edit feedback |  | Iteration 4 | Pending
28 | Delete Feedback | Admin, User | Simple | Allows user delete feedback |  | Iteration 4 | Pending
29 | Court Rating System | User, Admin | Medium | Allows user rating court |  | Iteration 4 | Pending
| 10800loc | 1 nguoi 1800-3600 | 1func/ 350